## Raw Data
2017 Job Cost, Margin and Commission Summary
[5 empty] | Totals to date |  | 5282725.9827 | 1771152.003 | 66.47% | 332281.8754 | 6.29% | 76729.89 | 11165.55 | 0
# | City | Designer | Installer | Contract Date | Customer | Product | Net Sale | Direct Costs | Margin | Comm $ | Comm % | Over (Under) Par | Addtl Incent | Credit Card Fees | Notes
| ABQ | MC | Sean | 2017-01-06 | Sandry | FP | 3594.18 | 2024.86 | 43.66% | 184.15 | 5.124% | -176.02 | 0 | under priced (by production) and under sized (by sales)
| RR | PB | Dennis | 2017-01-03 | Starkey | W | 6980.8 | 3164 | 54.68% | 831.66 | 11.91% | 395.2 | 0
| ABQ | PB | Don | 2017-01-16 | Albrecht | W | 4890.08 | 2609.27 | 46.64% | 370.95 | 7.586% | -67.02 | 0
| Rio Rancho | JG | Isaac | 2017-01-06 | Cordova | B | 6159.86 | 2573.13 | 58.23% | 787.99 | 12.79% | 473.76 | 0
| ABQ | PB | Russ T | 2017-01-17 | Maese | VP | 4938.85 | 2358.21 | 52.25% | 532.96 | 10.79% | 191.45 | 50
| ABQ | MC | Clay | 2017-01-09 | Hance | B | 8153.76 | 4414.86 | 45.85% | 756.02 | 9.272% | -104.63 | 0
| ABQ | MW | Russ T | 2017-01-19 | Kappus | LC | 2949.33 | 1467.24 | 50.25% | 328.77 | 11.15% | 128.33 | 0 | lattice tubes only
| Placitas | MW | ACSD | 2017-02-07 | Fox | B | 3049.41 | 1652 | 45.83% | 345.21 | 11.32% | 144.41 | 0 | cost $140 more than expected.
| ABQ | MC | Russ T | 2017-01-31 | Stitzel | FP | 5748.63 | 4321 | 24.83% | 397.22 | 6.91% | -482.87 | 100 | misguided pricing
| ABQ | MC | Clay | 2017-01-19 | Telles | B | 7077.46 | 3149.93 | 55.49% | 698.99 | 9.876% | -103.14 | 50
| ABQ | MW | Don | 2017-01-20 | Baca | LC | 3722.77 | 2289.64 | 38.5% | 387.89 | 10.42% | 187.77 | 0
| ABQ | MC | Isaac | 2017-01-17 | Riley | B | 7182.76 | 3382.89 | 52.9% | 542.12 | 7.548% | -865.14 | 200
| ABQ | PB | Don | 2017-01-24 | Tewanema | W | 7407.11 | 3637.54 | 50.89% | 665.98 | 8.991% | -125.59 | 0
| ABQ | MW | Russ T | 2017-01-24 | Rizzieri | Poly | 2981.95 | 1188.03 | 60.16% | 597.07 | 20.02% | 790.95 | 0
| ABQ | PB | Don | 2017-01-28 | Floyd | W | 14909.73 | 8127.97 | 45.49% | 1206.24 | 8.09% | -650.57 | 0
| ABQ | MC | Clay | 2017-02-18 | Owen | B | 15913.34 | 7202.21 | 54.74% | 1688.17 | 10.61% | 474.84 | 0
| ABQ | MW | Dennis | 2017-02-19 | Kappus | W | 20196.16 | 7838.8 | 61.19% | 3086.42 | 15.28% | 2883.26 | 0
| ABQ | MC | Clay | 2017-02-22 | Sousa | B | 6798.48 | 3032.04 | 55.4% | 750.86 | 11.04% | 221.28 | 0
| ABQ | MC | Isaac | 2017-02-08 | Collins | B | 6712.98 | 2994.88 | 55.39% | 639.87 | 9.532% | -112.32 | 50
| ABQ | PB | Russ T | 2017-02-14 | Cartales | VP | 7198.5 | 3681.21 | 48.86% | 556.12 | 7.725% | -365.6 | 0
| Bosque Farms | BO | Clay | 2017-02-26 | Garcia | B | 6109.76 | 2827.27 | 53.73% | 403.42 | 6.603% | -475.14 | 100
| ABQ | MW | Dennis | 2017-02-06 | Nulton | D | 7082.12 | 2978.28 | 57.95% | 951.12 | 13.43% | 677.28 | 0
| ABQ | PB | Clay | 2017-01-25 | Dodson | B-FR | 28999.42 | 16385.63 | 43.5% | 2018.01 | 6.959% | -253.58 | 0
| ABQ | MW | Marco | 2017-03-06 | Williams | FP | 7450.2 | 3347.96 | 55.06% | 823.6 | 11.05% | 454.4 | 0
| ABQ | MC | Marco | 2017-02-24 | Stamm | IR | 6085.96 | 2544.24 | 58.19% | 737.88 | 12.12% | 366.96 | 0
| Santa Fe | BO | Chris M | 2017-03-23 | Odell | B | 10097.27 | 4073.05 | 59.66% | 1168.07 | 11.57% | 614.61 | 0
| ABQ | MC | Cameron | 2017-02-21 | Wilde | FP | 7316.95 | 2762.01 | 62.25% | 943.45 | 12.89% | 573.15 | 0
| ABQ | MW | Marco | 2017-03-11 | Howard | IR | 6090.13 | 3148.5 | 48.3% | 671.37 | 11.02% | 252.13 | 0 | R&R gutter drip edge $70 cost, flashing factored into pricing?
| RR | MW | Russ T | 2017-03-01 | Krause | VP | 5973.52 | 2573.46 | 56.92% | 732.76 | 12.27% | 562.52 | 0 | cut pavers to fit around post, not dinged
| ABQ | GL | Clay | 2017-02-22 | Sousa | K | 5262.26 | 2844.64 | 45.94% | 521.95 | 9.919% | 163.06 | 0
| Roswell | JG | Marco | 2017-02-25 | Garcia | IR | 8802.33 | 4650.45 | 47.17% | 721.29 | 8.194% | -243.42 | 150 | Forgot 2nd story and footers
| RR | MW | Russ T | 2017-02-10 | Fox | SR-306 | 30955.54 | 13585.6 | 56.11% | 3222.73 | 10.41% | 1031.94 | 0
| Santa Fe | PB | Dennis | 2017-03-09 | Altman | W (A) | 8989.86 | 4365.47 | 51.44% | 777.23 | 8.646% | 302.42 | 50
| Los Lunas | PB | Don | 2017-03-18 | Aragon | W (A) | 7172.58 | 3008.1 | 58.06% | 842.38 | 11.74% | 832.38 | 0
| ABQ | PB | Don | 2017-03-06 | Lodal | W | 19755.39 | 10185.96 | 48.44% | 1287.43 | 6.517% | -1659.01 | 0
| ABQ | JG | Isaac | 2017-02-15 | Harwood | B | 11058.36 | 4701.71 | 57.48% | 1259.6 | 11.39% | 428.16 | 0 | swapping Clay for Isaac increased labor.
| ABQ | PB | Russ T | 2017-02-20 | Kavanaugh | VP | 6349.68 | 3379.95 | 46.77% | 521.42 | 8.212% | 3.48 | 0
| ABQ | JG | Isaac | 2017-01-25 | Wolfe | B | 8606.25 | 3558.71 | 58.65% | 916.82 | 10.65% | 246.75 | 0
| Bernalillo | MC | Chris M | 2017-03-16 | Garcia | B | 14070 | 5208.66 | 62.98% | 1635.44 | 11.62% | 664.79 | 0
| RR | SA | Dennis | 2017-03-29 | Chavez | W (A) | 3774.75 | 1451.33 | 61.55% | 505.04 | 13.38% | 255.15 | 50
| ABQ | MC | Chris M | 2017-03-07 | Handy | B | 9360.51 | 4216.53 | 54.95% | 517.96 | 5.533% | -1251.49 | 100
| Santa Fe | BO | Isaac | 2017-03-20 | Mauzy | B | 9116.82 | 4770.73 | 47.67% | 669.77 | 7.347% | -193.6 | 0
| ABQ | MW | Don | 2017-03-14 | McDaniel | W (A) | 3899.83 | 1545.61 | 60.37% | 466.89 | 11.97% | 490.83 | 0
| ABQ | JG | MS | 2017-03-15 | Allen | IR | 11938.36 | 5592.12 | 53.16% | 1343.32 | 11.25% | 573.76 | 0
| ABQ | GL | Clay | 2017-02-21 | Braddick | B-FR | 16870.27 | 9108.68 | 46.01% | 1569.67 | 9.304% | 1337.97 | 200 | Costs higher than anticipated
| San Felipe | BO | Chris M | 2017-03-21 | Aguilar | B | 7436.51 | 2416.03 | 67.51% | 891.66 | 11.99% | 492.51 | 0
| ABQ | PB | Marco | 2017-03-07 | Pickrell | SR-VV | 8947.89 | 3308.62 | 63.02% | 737.85 | 8.246% | -726.11 | 200
| RR | PB | Marco | 2017-03-16 | Zelasko | IR | 4530.2 | 2250.77 | 50.32% | 447.9 | 9.887% | 92.2 | 0
| Santa Fe | GL | Clay | 2017-03-15 | Zrakovi | B | 10078.25 | 5206.72 | 48.34% | 899.81 | 8.928% | -122.15 | 0
| ABQ | MW | Russ T | 2017-02-01 | Pfau/Nulton | SR-VV | 27722.77 | 12664.96 | 54.32% | 1891.81 | 6.824% | -1877.43 | 0
| ABQ | MW | Marco | 2017-03-22 | Leonard | IR | 5870.7 | 3074.75 | 47.63% | 540.65 | 9.209% | -72.3 | 0
| Santa Fe | PB | Don | 2017-03-31 | Scalise | W (A) | 16931.07 | 7903.44 | 53.32% | 572.57 | 3.382% | -1363.25 | 0
| ABQ | PB | Dennis | 2017-02-11 | Alarid | W (A) | 7738.35 | 4758.71 | 38.5% | 338.87 | 4.379% | -876.65 | 0 | Front half payed at 10% in error
| Santa Fe | PB | Dennis | 2017-03-31 | Gardopee | W (A) | 5187.77 | 2430.88 | 53.14% | 274.99 | 5.301% | -142.38 | 0
| Santa Fe | PB | Marco | 2017-04-03 | Miramontes | SR-306 | 10413.05 | 5283.01 | 49.27% | 840.1 | 8.068% | -354.35 | 0
| RR | MW | Marco | 2017-02-28 | Bergsten | SR-306 | 36253.64 | 18839.26 | 48.03% | 2423.79 | 6.686% | 576.74 | 0
| ABQ | BO | Chris M | 2017-03-22 | Rogers | B | 9646.55 | 3544.5 | 63.26% | 1005.34 | 10.42% | 166.45 | 0
| ABQ | PB | Don | 2017-04-06 | Clements | D | 3816.17 | 2302.09 | 39.68% | 310.83 | 8.145% | -115.73 | 0
| ABQ | GL | Isaac | 2017-02-25 | Macdonnell | B | 9149.76 | 4366.08 | 52.28% | 486.18 | 5.314% | 1028.24 | 0
| ABQ | GL | Clay | 2017-02-22 | Cormier | B-FR | 23476.6 | 13920.04 | 40.71% | 1295.49 | 5.518% | -1217.3 | 0 | Cost was $2170 higher than expected
| ABQ | JG | Chris M | 2017-03-21 | Ward | B-FR | 22560.96 | 11895.35 | 47.27% | 193.57 | 0.858% | -5110.08 | 400
| RR | MW | Marco | 2017-03-30 | McCart | PC | 11076.21 | 4764.92 | 56.98% | 1086.1 | 9.806% | 156.21 | 0
| Bernalillo | JG | Isaac | 2017-03-25 | Broussard | B | 7187.03 | 3093.23 | 56.96% | 623.41 | 8.674% | -197.47 | 0
| RR | GL | Chris M | 2017-03-29 | Guillen | K | 17785.22 | 11150.37 | 37.31% | 460.97 | 2.592% | 3167.18 | 200 | Cost was $2000 higher than expected
| Belen | JG | Russ T | 2017-04-24 | Cabral | PC | 4586.59 | 2841.94 | 38.04% | 156.19 | 3.405% | -208.41 | 0 | Cost of concrete was $190 more than par
| ABQ | JG | Russ T | 2017-03-10 | Jessa | PC | 13017.12 | 5758.63 | 55.76% | 1033.86 | 7.942% | -407.13 | 0
| ABQ | PB | Marco | 2017-04-10 | Hattar | IR | 11788 | 8428.75 | 28.5% | 513.3 | 4.354% | -547 | 0 | Cost was $2534 higher than expected
| Los Lunas | PB | Russ T | 2017-02-28 | Zimmerman | FP | 7433.35 | 4289.65 | 42.29% | 219.61 | 2.954% | -711.15 | 0
| ABQ | MC | Russ T | 2017-03-13 | Chavez | SR-206 | 14909.73 | 6559.46 | 56.01% | 1459.08 | 9.786% | 261.53 | 0
| Santa Fe | PB | Dennis | 2017-04-26 | LaPlantz | W | 5651.15 | 3226.62 | 42.9% | 790.07 | 13.98% | 1023.78 | 0 | CO for $2,046.73 added as non-comm
| ABQ | MW | Marco | 2017-04-14 | Torrez | IR | 6499.71 | 2708.39 | 58.33% | 721.03 | 11.09% | 413.91 | 0
| Sandia Park | SA | Isaac | 2017-04-03 | Ring | B | 7979.29 | 4078.61 | 48.89% | 819.67 | 10.27% | 198.11 | 0 | Adjustments added for unexpected costs
| RR | JG | Cameron | 2017-04-01 | Tirone | LC | 6915.21 | 4057.71 | 41.32% | 371.45 | 5.371% | -157.59 | 0 | Costs were $600 higher than expected (Concrete cost $1920)
| Santa Fe | PB | Dennis | 2017-04-17 | Flores | D | 4312.85 | 2438.64 | 43.46% | 354.24 | 8.214% | -98.9 | 0 | Costs were $282 higher than expected ($110 @ THD)
| RR | MW | Marco | 2017-03-21 | Bowen | SR-VV | 5584.64 | 2153.62 | 61.44% | 596.72 | 10.69% | 110.64 | 50 | Costs were $639 less than expected
| ABQ | JG | Russ T | 2017-04-24 | Florence | VP | 9597.95 | 4312.64 | 55.07% | 1193.55 | 12.44% | 806.65 | 0 | Costs were $486 less than expected
| Rio Rancho | JG | Clay | 2017-03-21 | Kitchen | B-FR | 26823.04 | 12239.5 | 54.37% | 3261.58 | 12.16% | 1491.94 | 0
| Bernalillo | MC | Marco | 2017-05-02 | Abby/McEneany | LC | 7193.93 | 3563.32 | 50.47% | 1033.14 | 14.36% | 1298.53 | 0
| ABQ | GL | Chris M | 2017-04-03 | Chavez | B-FR | 14178.77 | 6750.83 | 52.39% | 1368.88 | 9.654% | -328.73 | 100 | (Job Cost(s) added: 01/04/2018)
| ABQ | GL | Clay | 2017-03-31 | Polster | K | 16349.94 | 8687.94 | 46.86% | 1830.82 | 11.2% | 859.64 | 0
| Clovis | JG | Dennis | 2017-04-08 | Curtis | IR | 11303.06 | 7108.84 | 37.11% | 545.24 | 4.824% | -263.6 | 138.12 | Costs were $1457 higher than expected (Hotel/Mileage - SGD)
| Rio Rancho | SA | Clay | 2017-04-07 | Schultz | B | 10340.9 | 3779 | 63.46% | 1674.79 | 16.2% | 1645.5 | 0
| ABQ | PB | Russ T | 2017-04-14 | Sidhu | VP | 3331.39 | 1637.64 | 50.84% | 403.18 | 12.1% | 219.47 | 0
| ABQ | PB | Russ T | 2017-03-15 | Porter | SR-VV | 8945.84 | 3443.99 | 61.5% | 605.42 | 6.768% | -609.16 | 0
| Rio Rancho | SA | Isaac | 2017-04-04 | Rice | B | 9300.29 | 3374.98 | 63.71% | 1947.17 | 20.94% | 2586.59 | 0
| Clovis | JG | Clay | 2017-04-18 | Fetzer | B | 9500.06 | 4570.75 | 51.89% | 909.51 | 9.574% | 363.31 | 0
| RR | MW | Russ T | 2017-04-21 | Nicko | IR | 8190.81 | 4247.25 | 48.15% | 485.08 | 5.922% | -729.99 | 0
| RR | PB | Marco | 2017-04-12 | Irizarri | OP | 15795.56 | 8721.39 | 44.79% | 1346.62 | 8.525% | -358.34 | 0 | Costs were $823 higher than expected (our 1st op perg)
| Santa Fe | LE | Isaac | 2017-05-02 | Facteau | B | 6608.81 | 3476.36 | 47.4% | 709.7 | 10.74% | 219.71 | 0 | Costs were $172 higher than expected. LE didn't charge for Onyx appropirately
| RR | JG | Marco | 2017-04-14 | Charlee | LC | 5587.26 | 3473.15 | 37.84% | 389.83 | 6.977% | 55.16 | 0 | Costs were $680 higher than expected. Concrete cost = PAR
| ABQ | MW | Chris M | 2017-03-18 | Longstreet | B-FR | 15954.61 | 7185.86 | 54.96% | 1716.53 | 10.76% | 346.43 | 0
| ABQ | PB | Don | 2017-02-07 | Hussey | W | 20626.67 | 10063.1 | 51.21% | 2470.58 | 11.98% | 1243.27 | 0
| Clovis | JG | Clay | 2017-04-05 | Winkenweder | B-FR | 18668.83 | 8408.98 | 54.96% | 1594.72 | 8.542% | -163.97 | 0
| ABQ | MW | Don | 2017-05-01 | Ferrance | W | 4100.17 | 1782.32 | 56.53% | 578.27 | 14.1% | 726.87 | 0
| ABQ | MW | Russ T | 2017-05-01 | Ferrance | LC | 9877.69 | 5228.38 | 47.07% | 1165.92 | 11.8% | 718.37 | 0 | Error at CABQ charged us $945.67 for permitting. Refund will be issued, amount unknown
| ABQ | MC | Marco | 2017-04-28 | Shelton | LC | 4203.1 | 1577.68 | 62.46% | 648.35 | 15.43% | 717.11 | 0
| RR | MW | Marco | 2017-05-15 | Kitele | IR | 16125.65 | 7920.51 | 50.88% | 1249.87 | 7.751% | -38.75 | 0
| ABQ | PB | Don | 2017-05-12 | Buchanan | D | 12761.79 | 7782.9 | 39.01% | 381 | 2.985% | -3903.81 | 690.84 | Costs were $1402 higher than expected (Was labor factored into product pricing?)
| ABQ | SA | Clay | 2017-04-06 | Miera | B | 11705.07 | 6909.76 | 40.97% | 939.98 | 8.031% | -532.56 | 0 | Costs were $1057 higher than expected ($606 in service fees to change out tile + tile factored @ $40, not $50)
| ABQ | MW | Russ T | 2017-03-27 | Narvais | LC | 8386.72 | 6831.75 | 18.54% | 894.32 | 10.66% | -2792.08 | 1530.74 | Had to re-do PC to avoid major customer repercussions
| Sandia Park | GL | Isaac | 2017-04-22 | Piper | B | 17600 | 9930.71 | 43.58% | 962.1 | 5.466% | -1541.5 | 0 | Costs were $1131 higher than expected ($561 in CC fees - $441 to re-order shower door glass - $982 spent @ TH - Toilet Replaced? )
| Los Lunas | SA | Cameron | 2017-06-13 | Lopez | FP | 8090.48 | 2852.4 | 64.74% | 854.08 | 10.56% | 217.58 | 0
| ABQ | MW | Don | 2017-06-03 | Romero | VP | 13511.94 | 4693.83 | 65.26% | 1207 | 8.933% | -16.96 | 0
| ABQ | House | Clay | 2017-07-12 | Lundy | B | 1000.93 | 454.15 | 54.63% | 0 | 0% | 0 | 0 | Service, No Comm
| ABQ | GL | Isaac | 2017-07-07 | Holbrook | D | 1220.47 | 628.79 | 48.48% | 268.35 | 21.99% | 365.77 | 0 | Costs were $18 higher than expected ($19.68 in CC fees)
| RR | MW | House | 2017-04-07 | Carey | SR-206 | 3251.52 | 719.61 | 77.87% | 378.02 | 11.63% | 175.93 | 0 | Install done by Anthony & Richard
| ABQ | JG | Cameron | 2017-05-31 | Otahal | FP | 6843.56 | 3274.53 | 52.15% | 600.78 | 8.779% | -103.94 | 0
| ABQ | PB | Don | 2017-06-10 | Elmquist | W (A) | 7989.75 | 3799.45 | 52.45% | 642.04 | 8.036% | 232.35 | 0
| ABQ | SA | Isaac | 2017-05-10 | O'Neal | B | 13472.8 | 6191.73 | 54.04% | 1823.94 | 13.54% | 1235.4 | 0
| ABQ | MW | Marco | 2017-05-06 | Potutschnig | IR | 11927.78 | 6931.01 | 41.89% | 824.49 | 6.912% | 75.38 | 0 | Costs were $967 higher than expected (Concrete more than expected, Permit more than accounted for)
| ABQ | MW | Cameron | 2017-05-09 | Johns | IR | 6429.82 | 2832.3 | 55.95% | 603.91 | 9.392% | -24.18 | 0
| ABQ | MW | Don | 2017-06-20 | Ezzell | D | 6476.41 | 3597.7 | 44.45% | 568.88 | 8.784% | 308.57 | 0 | Costs were $359 higher than expected ($208.5 in CC fees, Stucco patch not accounted for)
| Rio Rancho | ME | Isaac | 2017-05-22 | Bella | B | 6331.93 | 2917.38 | 53.93% | 812.99 | 12.84% | 514.23 | 0
| ABQ | MW | Marco | 2017-05-11 | Griego | IR | 11555.04 | 5877.16 | 49.14% | 1059.52 | 9.169% | 390.74 | 0
| Tijeras | PB | Russ T | 2017-04-23 | Franowski | OP | 29082.35 | 18337.2 | 36.95% | 1846.96 | 6.351% | -1205.95 | 0 | Cost of materials much higher than calculated
| Clovis | JG | Custom Fit | 2017-04-18 | Fetzer, T | Siding | 29464.43 | 15300.58 | 48.07% | 2717.45 | 9.223% | 13.96 | 0
| ABQ | GL | Clay | 2017-04-12 | Gerlach | B | 13812.93 | 8567.38 | 37.98% | 997.88 | 7.224% | -819.77 | 0 | (Job Cost(s) added: 01/04/2018)
| Ruidoso | PB | Marco | 2017-03-21 | Wright | OP | 8507.2 | 5911.07 | 30.52% | 416.99 | 4.902% | -632.95 | 0
| ABQ | JG | Russ T | 2017-04-30 | Williams | OP | 10055.68 | 5877.07 | 41.55% | 644.92 | 6.413% | -724.62 | 0
| Santa Fe | PB | Dennis | 2017-06-06 | Siegel | W | 13457.94 | 7010.8 | 47.91% | 878.86 | 6.53% | -890.11 | 0 | Stucco patch/trim out not accounted for on comm sheet
| ABQ | JG | Marco | 2017-04-25 | Trombino | IR | 13762.61 | 6734.96 | 51.06% | 1516.5 | 11.02% | 840.61 | 0
| ABQ | SA | Don | 2017-06-15 | Granone | W | 9352.13 | 4905.42 | 47.55% | 766.48 | 8.196% | -190.57 | 0 | Stucco patch/shutters not accounted for on comm sheet
| ABQ | AP | Isaac | 2017-05-25 | Doft | B | 10327.78 | 5218.47 | 49.47% | 1373.39 | 13.3% | 895.28 | 0 | $166 in CC fees, $441 @ THD
| ABQ | MW | Dennis | 2017-06-17 | Eckstein | W (A) | 6476.41 | 2527.86 | 60.97% | 934.84 | 14.43% | 1216.61 | 0
| ABQ | MW | Russ T | 2017-04-13 | Wills | IR | 21035.12 | 12362.54 | 41.23% | 2004.67 | 9.53% | 412.15 | 0 | Comm sheet adjusted to include additional work
| ABQ | House | Chris M | 2017-05-14 | Thompson | B | 12114.15 | 6567.93 | 45.78% | 0 | 0% | 0 | 0
| RR | MC | Cameron | 2017-06-07 | Marsico | FP | 6056.58 | 2432.1 | 59.84% | 587.25 | 9.696% | 58.98 | 0
| ABQ | MW | Cameron | 2017-05-19 | Hewitt | LC | 5777.52 | 2386.32 | 58.7% | 661.92 | 11.46% | 357.42 | 0
| Los Lunas | PB | Russ T | 2017-05-06 | Baca | IR | 8185.09 | 4097.27 | 49.94% | 798.35 | 9.754% | 23.09 | 0
| Espanola | JG | Russ T | 2017-05-01 | Marquez | IR | 12731.15 | 5314.15 | 58.26% | 1523.58 | 11.97% | 727.09 | 0
| ABQ | MW | Don | 2017-03-29 | DiLorenzo | W | 13977.87 | 7544.79 | 46.02% | 1178.74 | 8.433% | -427.53 | 0 | $1000 discount given, Per Jack. Plus ,$181 for Handi-Ramp
| ABQ | ME | Isaac | 2017-05-22 | Losee | B | 7597.12 | 3816.36 | 49.77% | 718.7 | 9.46% | -58.78 | 0
| ABQ | SA | Cameron | 2017-05-17 | Welch | PC | 5494.23 | 3494.46 | 36.4% | 516.08 | 9.393% | 357.63 | 0
| ABQ | MW | Robert T | 2017-06-20 | Young | Roof | 999.88 | 506.14 | 49.38% | 244.44 | 24.45% | 404.88 | 0
| Rio Rancho | LE | Chris M | 2017-05-22 | Keeler | B | 8050.26 | 4196.55 | 47.87% | 1451.68 | 18.03% | 1712.88 | 0 | $500 discount
| ABQ | JG | Cameron | 2017-06-14 | Sellers | FP | 12141.18 | 4596.03 | 62.15% | 1111.23 | 9.153% | -152.22 | 0
| ABQ | SA | Cameron | 2017-06-15 | Granone | LC | 5261.27 | 2939.67 | 44.13% | 346.29 | 6.582% | -320.03 | 0 | Costs were $309 higher than expected ($264 in CC fees)
| ABQ | MW | Russ T | 2017-06-26 | Addy | IR | 6057.08 | 2661.05 | 56.07% | 673.04 | 11.11% | 212.08 | 0
| RR | GL | Prime Time | 2017-04-17 | Webb | K | 16553.81 | 10892.86 | 34.2% | 581.19 | 3.511% | 1680.49 | 190.04 | Costs were $2616 higher than expected. Contract credited $923 for blind pull-outs ($534 in CC fees, $863 for plumbing)
| ABQ | LE | Marco | 2017-06-05 | Scott | FP | 5897.78 | 2619.52 | 55.58% | 875.64 | 14.85% | 900.13 | 0 | Split up commission on Back half (was FP/B sold together)
| ABQ | JG | Don | 2017-06-24 | Masten | W | 21881.84 | 10126.01 | 53.72% | 2838.7 | 12.97% | 1687.54 | 0
| ABQ | PB | Cameron | 2017-05-19 | Clack | LC | 11508.44 | 5461.99 | 52.54% | 1192.04 | 10.36% | 146.74 | 0
| ABQ | MW | Cameron | 2017-07-20 | Masters | LC | 3348.84 | 1163.3 | 65.26% | 368.22 | 11% | 156.84 | 0
| ABQ | LE | Chris M | 2017-05-27 | Hunt (B) | B | 10407.92 | 3715.32 | 64.3% | 2920.98 | 28.06% | 4744.22 | 0 | Split contract 50/50 for closing: Bath/Lattice Cover
| ABQ | ME | Mike R | 2017-06-13 | Sierra | B | 10862.44 | 5579.03 | 48.64% | 1087.38 | 10.01% | 1077.84 | 0 | Costs were $564 higher than expected. ($1397 spent @ Home Depot)
| Placitas | GL | Chris M | 2017-03-28 | Rossi | D | 1212.24 | 817.51 | 32.56% | 160.78 | 13.26% | 62.64 | 0 | The labor of installing a shower door ($250) is 20% of net
| ABQ | GL | Isaac | 2017-07-03 | Clack | B | 1753.49 | 703.91 | 59.86% | 286.09 | 16.32% | 320.59 | 0 | $200 discount given at time of final payment for "Not meeting timeline"
| Placitas | MW | Cameron | 2017-07-18 | Howser | LC | 4658.82 | 1983.49 | 57.43% | 400.91 | 8.605% | -59.18 | 0
| Clovis | JG | Isaac | 2017-05-26 | Bright | B | 8696.6 | 4605.7 | 47.04% | 649.47 | 7.468% | -75.45 | 0
| ABQ | MW | Marco | 2017-07-19 | Saiz | LC | 6093.02 | 3527.04 | 42.11% | 492.21 | 8.078% | -248.98 | 0 | Costs were $480 more than expected: $196 in CC charges, and under par.
| ABQ | MW | Don | 2017-07-17 | McCament-Mann | D | 7348.84 | 3677.07 | 49.96% | 734.2 | 9.991% | 72.04 | 0
| ABQ | NM | Russ T | 2017-07-24 | Klinetobe | LC | 7906.98 | 3387.68 | 57.16% | 902.05 | 11.41% | 394.13 | 0 | Job Cost(s) added: 01/04/2018)
| Edgewood | SA | Dennis | 2017-06-27 | Haslam | W (A) | 2575.7 | 1256.6 | 51.21% | 196.13 | 7.615% | 76.7 | 0
| ABQ | PB | Robert T | 2017-03-15 | Makowski | LC | 9048.34 | 4912.66 | 45.71% | 629.8 | 6.96% | -745.1 | 100
| Tijeras | LE | Chris M | 2017-04-27 | Aragon | B-FR | 16461.88 | 7132.31 | 56.67% | 2983.04 | 18.12% | 3385.88 | 0 | Customer canceled financing and paid in cash
| ABQ | MW | Cameron | 2017-06-15 | ARCA 1 | VP | 8400 | 3165.41 | 62.32% | 941.68 | 11.21% | 109.2 | 0
| ABQ | MW | Russ T | 2017-06-06 | Lacy | SR-206 | 22654.62 | 7855.95 | 65.32% | 2661.87 | 11.75% | 1743.52 | 0
| Los Alamos | MW | Marco | 2017-04-26 | Montoya | SR-306 | 42201.05 | 20488.3 | 51.45% | 3646.02 | 8.64% | 2106.87 | 0 | Job Cost(s) added: 01/04/2018)
| Santa Fe | MW | Don | 2017-08-07 | Wolfe | W | 3462.2 | 1369.18 | 60.45% | 512.67 | 14.81% | 507.9 | 0
| Santa Fe | PB | Marco | 2017-06-12 | Oppenheimer | IR | 14495.1 | 12408.59 | 14.39% | 371.65 | 2.564% | -5410.6 | 2057.96 | Concrete work cost was $6300 (Par calc at $3561)
| ABQ | SA | Don | 2017-07-08 | Yamashita | W | 6277.08 | 2545.17 | 59.45% | 777.44 | 12.39% | 435.58 | 0
| Edgewood | GL | Prime Time | 2017-06-30 | Robinson | K | 22029.84 | 13551.24 | 38.49% | 1127.61 | 5.119% | -1799.27 | 0 | Costs were $1418 higher than expected ($714 in CC fees, $362 in storage fees, $390 in unforseen cost) Job Cost(s) added: 01/04/2018)
| ABQ | GL | Clay | 2017-04-27 | Welles | K | 56657.89 | 32507.87 | 42.62% | 6206.89 | 10.96% | 2823.49 | 0 | Costs were $1967 higher than expected ($1364 in CC fees, $420 in storage fees, Electrical and Dumpster) Job Cost(s) added: 01/04/2018)
| ABQ | LE | Chris M | 2017-05-18 | Sigal | B | 18131.16 | 8614.07 | 52.49% | 1647.12 | 9.084% | -371.24 | 0
| ABQ | JG | Isaac | 2017-06-27 | Burton | B | 9695.98 | 3703.14 | 61.81% | 993.37 | 10.25% | 120.68 | 0
| ABQ | MW | Russ T | 2017-04-08 | Goff | SR-306 | 38509.74 | 15043.63 | 60.94% | 5035.12 | 13.07% | 3518.62 | 0
| ABQ | MW | Don | 2017-08-08 | Mullins | D | 3627.91 | 1469.66 | 59.49% | 278.96 | 7.689% | 223.39 | 0
| ABQ | LE | Isaac | 2017-06-07 | Arnold | B | 7781.95 | 2757.3 | 64.57% | 1227.28 | 15.77% | 1166.46 | 0
| ABQ | LE | Isaac | 2017-05-19 | Adair | B | 9955.97 | 5346.63 | 46.3% | 922.52 | 9.266% | 332.05 | 0 | C/O Priced short Adjusted commission. Cost was $369 high.
| Santa Fe | JG | Dennis | 2017-06-17 | Bartell/Lujan | W | 14345.55 | 10877.21 | 24.18% | 747 | 5.207% | -2133.65 | 507.83 | Bay window/PD Needed structural framing, stucco work add'l travel
| Sandia Park | SA | Don | 2017-07-24 | Hancock | W (A) | 2572.35 | 1297.58 | 49.56% | 183.32 | 7.127% | 76.75 | 0
| ABQ | LE | Chris M | 2017-06-05 | Scott | B-FR | 17693.32 | 6705.56 | 62.1% | 3180.16 | 17.97% | 3570.82 | 0
| Edgewood | MW | Marco | 2017-07-29 | Lopez | IR | 7884.09 | 3261.43 | 58.63% | 1008.7 | 12.79% | 600.59 | 0
| ABQ | MW | Russ T | 2017-08-05 | Brown | IR | 7271.63 | 3348.22 | 53.96% | 779.12 | 10.71% | 243.63 | 0
| ABQ | MW | Cameron | 2017-07-28 | Bailey | LC | 3813.95 | 1775.34 | 53.45% | 368.8 | 9.67% | 81.55 | 0
| ABQ | MW | Cameron | 2017-06-19 | ARCA 2 | VP | 9100 | 3761.43 | 58.67% | 954.24 | 10.49% | 366.1 | 0 | Job Cost(s) added: 01/04/2018)
| ABQ | JG | Isaac | 2017-08-15 | Ruthardt/Cosme | B | 3942.33 | 2248.27 | 42.97% | 329.16 | 8.349% | 59.83 | 0 | Costs were $277 higher than expected ($64 in CC fees and over $200 more on install))
| ABQ | LE | Isaac | 2017-07-01 | Koski | B | 8097.73 | 3657.75 | 54.83% | 732.25 | 9.043% | -731.79 | 232.69 | Customer did not pay in full (-$500) Over/under includes deficiency
| ABQ | LE | Russ T | 2017-05-27 | Hunt(LC) | LC | 10407.92 | 3331.15 | 67.99% | 2636.08 | 25.33% | 4107.92 | 0 | Split contract 50/50 for closing: Bath/Lattice Cover
| RR | MC | Marco | 2017-08-02 | Chace | LC | 7211.6347 | 4170.75 | 42.17% | 576.7973 | 7.998% | -195.1653 | 0 | C/O to remove 2 footers, customer poured own, they were incorrect: C/O added to remove cust footers and pour our own
| ABQ | MC | Marco | 2017-09-05 | Wilson | FP | 4098.6 | 1738.81 | 57.58% | 377.7 | 9.215% | 24.6 | 0
| RR | MW | Russ T | 2017-06-09 | Wolters | Roof | 8563.12 | 4178.77 | 51.2% | 995.48 | 11.63% | 688.12 | 0 | (Replacing roof on SR) Electric cost over double expected - wiring had to be re-done
| ABQ | MW | Marco | 2017-07-10 | Kishbaugh | IR | 9023.26 | 5237.41 | 41.96% | 662.4 | 7.341% | -28.44 | 0 | Costs were 725 higher than expected: Demo/remove spa Cost $260 more, Add'l work needed to be done by Marco, 2nd story fee)
| Belen | JG | Don | 2017-05-09 | Ruz | W (A) | 2500 | 2152.05 | 13.92% | 11.47 | 0.4588% | -372.15 | 82.1 | Incorrectly sold + $200 discount to customer
| ABQ | MW | Marco | 2017-08-21 | Sorensen | LC | 7610.1 | 3367.87 | 55.74% | 858.47 | 11.28% | 514.9 | 0
| ABQ | GL | Isaac | 2017-04-26 | Payne | B-FR | 82840.13 | 47278.75 | 42.93% | 6217.09 | 7.505% | -3023.92 | 0 | Costs were $5157 higher than expected (Electrical: $3399 add'l, Plumbing: $2239 add'l, Tile: $684 add'l. (Job Cost(s) added: 01/04/2018)
| Farmington | JG | Isaac | 2017-08-21 | Harrison | B | 8717.42 | 4550.29 | 47.8% | 868.44 | 9.962% | 508.52 | 0
| Placitas | MW | Robert T | 2017-08-16 | Domenick/English | Poly | 7642.35 | 2196.41 | 71.26% | 1003.68 | 13.13% | 642.35 | 0
| ABQ | GL | Chris M | 2017-06-03 | Lowe | B | 13169.73 | 5401.9 | 58.98% | 1881.29 | 14.28% | 1454.53 | 0 | Job Cost(s) added: 01/04/2018)
| ABQ | JG | Chris M | 2017-09-07 | Thorne | B | 10692.66 | 4540.69 | 57.53% | 1049.03 | 9.811% | -6.84 | 0
| ABQ | MW | Marco | 2017-09-11 | Giron | IR | 6413.95 | 3032.2 | 52.72% | 612.78 | 9.554% | 134.95 | 0
| RR | MW | Don | 2017-08-25 | Schultz | D | 6143.11 | 2994.75 | 51.25% | 646.89 | 10.53% | 142.71 | 0
| Farmington | JG | Isaac | 2017-08-30 | Brown | B | 9984.67 | 5382.12 | 46.1% | 808.81 | 8.101% | -60.23 | 17.13 | Travel/mileage omitted from front end calc - Work took 1 extra day
| ABQ | GL | Chris M | 2017-07-20 | Silva | B-FR | 30094.31 | 11919.41 | 60.39% | 3095.64 | 10.29% | 303.01 | 0
| ABQ | MC | Marco | 2017-08-29 | Wilde | FP | 4748.84 | 3828.53 | 19.38% | 224.95 | 4.737% | -692.16 | 157.33 | Adding to existing car port - new cover needed to be free-standing. Footers needed to be very large per code
| RR | MW | Marco | 2017-08-24 | Rose | IR | 6841.19 | 4154.79 | 39.27% | 293.39 | 4.289% | -216.81 | 0 | Costs were $734 higher than expected. (Permitted concrete, needed 10" turndown)
| ABQ | PB | Don | 2017-07-06 | Akins | D | 4000 | 1814.86 | 54.63% | 343.91 | 8.598% | 188.5 | 0
| ABQ | PB | Robert T | 2017-04-20 | Maez Constr. | Poly | 1751.89 | 765.96 | 56.28% | 200.45 | 11.44% | 106.89 | 0
| RR | MW | Russ T | 2017-07-10 | Vaughn | SR-VV | 11388.9 | 4883.62 | 57.12% | 922.83 | 8.103% | 165.1 | 0
| ABQ | MW | Russ T | 2017-07-15 | Linderman/Timms | IR | 9944.19 | 4864.97 | 51.08% | 1044.54 | 10.5% | 373.79 | 0
| ABQ | PB | Russ T | 2017-07-12 | Abeyta | SR-306 | 46511.63 | 25137.84 | 45.95% | 2209.49 | 4.75% | -2576.67 | 0 | Costs were 1882 higher than expected (Concrete)
| Los Alamos | PB | Dennis | 2017-06-28 | Brewer | W | 5008.74 | 2788.84 | 44.32% | 471.13 | 9.406% | 89.24 | 0 | Costs were $285 higher than expected
| ABQ | MW | Russ T | 2017-09-22 | Carriaga | IR | 17441.86 | 8726 | 49.97% | 1696.71 | 9.728% | 1514.06 | 0
| ABQ | MW | Russ T | 2017-09-19 | Dranberg | IR | 5581.4 | 2176.81 | 61% | 782.4 | 14.02% | 604.4 | 0
| ABQ | LE | Chris M | 2017-09-19 | Vogel | B | 5476.17 | 2158.82 | 60.58% | 777.1 | 14.19% | 617.47 | 0
| ABQ | JG | Russ T | 2017-10-10 | Busboom | SR-VV | 5890.87 | 2373.11 | 59.72% | 1044.09 | 17.72% | 1181.27 | 0
| Santa Fe | GL | Clay | 2017-06-27 | Dunn | B-FR | 16895.5568 | 7362.42 | 56.42% | 1789.5184 | 10.59% | 395.1568 | 0
| Estancia | MW | Don | 2017-09-15 | Alarid | W (A) | 9514.85 | 4255.85 | 55.27% | 852.23 | 8.957% | 519.15 | 0
| Farmington | JG | Marco | 2017-08-18 | Krob | IR | 9105.69 | 5855.16 | 35.7% | 316.42 | 3.475% | -1036.61 | 8.79 | $700 discount given @ completion - Originally sold @ $386 under par
| ABQ | MW | Don | 2017-08-21 | Chando | D | 5206.85 | 2226.1 | 57.25% | 503.27 | 9.666% | 17.72 | 0
| ABQ | MW | Russ T | 2017-10-16 | Goodrich | IR | 4557.21 | 2398.28 | 47.37% | 564.3 | 12.38% | 315.21 | 0 | $100 discount given at closing for not capping gutter (discount should not have been given as customer wasn't charged for capping gutter on the contract) $200 spent at THD
| ABQ | GL | Chris M | 2017-08-07 | Kindred | K | 15092.09 | 7345.92 | 51.33% | 1925.05 | 12.76% | 1127.09 | 0 | Job Cost(s) added: 01/04/2018)
| ABQ | MW | Don | 2017-08-29 | Herrington | W | 17669.77 | 8127.79 | 54% | 1785.18 | 10.1% | 106.77 | 0
| RR | MW | Marco | 2017-08-02 | Wade | SR-306 | 25447.35 | 13087.28 | 48.57% | 2051.18 | 8.06% | 322.35 | 0
| Elephant Butte | JG | Don | 2017-09-19 | Everett | W | 15612.71 | 8884.49 | 43.09% | 833.79 | 5.34% | -945.79 | 0 | Broken window service call: $470.20 Margin. Change added: 01/04/2018)
| ABQ | GL | Chris M | 2017-08-15 | Gagon-Olson | K | 21894.88 | 14591.51 | 33.36% | 836.23 | 3.819% | -1450.22 | 0 | Over 5,000 comm should have been non-comm or was underpriced.
| Santo Domingo | JG | Chris M | 2017-10-03 | Bailon | B | 5972 | 2636.54 | 55.85% | 772.67 | 12.94% | 519 | 0
| ABQ | GL | Isaac | 2017-05-30 | Piegzik | B-FR | 29302.2714 | 21160.08 | 27.79% | 1738.1157 | 5.932% | -2409.9286 | 0 | Plumbing and tile was $4500 more than expected (retail) Job Cost(s) added: 01/04/2018)
| ABQ | JG | Don | 2017-09-26 | Byers-Smith | D | 2409.35 | 1093.81 | 54.6% | 200.175 | 8.308% | -40.65 | 0
| ABQ | JG | Russ T | 2017-06-12 | Schulte | LC | 5098.19 | 2286.75 | 55.15% | 683.65 | 13.41% | 539.58 | 0
| Tijeras | MW | Russ T | 2017-09-06 | Herring/Claypool | SR-306 | 16475.3 | 7849.77 | 52.35% | 1066.29 | 6.472% | -1103.1 | 0
| ABQ | JG | Don | 2017-08-15 | Moore | Siding | 20847.4 | 11258.68 | 45.99% | 1319.96 | 6.332% | -1655.7 | 0 | Costs of siding material/labor were $780 higher than priced
| ABQ | JG | Isaac | 2017-10-02 | Smith | B | 8163.72 | 3753.49 | 54.02% | 827.84 | 10.14% | 72.42 | 0
| Tijeras | MW | Marco | 2017-09-26 | Heffenger | SR-206 | 21045.21 | 8072.36 | 61.64% | 2340.39 | 11.12% | 1270.21 | 0
| ABQ | GL | Chris M | 2017-09-15 | Jimenez/Rhine | K | 30219.08 | 16478.26 | 45.47% | 2449 | 8.104% | -107.42 | 0 | Job Cost(s) added: 01/04/2018)
| Los Alamos | MW | Russ T | 2017-09-01 | Fugard | IR | 23599.3 | 11799.96 | 50% | 1719.65 | 7.287% | 1423.3 | 0
| ABQ | LE | Isaac | 2017-09-18 | McNeal | B | 14260.26 | 7210.8 | 49.43% | 1528.53 | 10.72% | 741.36 | 0
| RR | JG | Eric | 2017-10-10 | Busboom/Fullam | Siding | 5025.2472 | 3075.84 | 38.79% | 404.06 | 8.041% | -297.25 | 148.84 | Costs of siding material/labor were $1105 higher than priced
| ABQ | JG | Marco | 2017-11-07 | Doyle | LC | 4117.0015 | 1970.34 | 52.14% | 509.5408 | 12.38% | 288.3515 | 0
| Santa Fe | JG | Russ T | 2017-09-25 | Hewitt | B-FR | 48571.08 | 24082.29 | 50.42% | 4876.43 | 10.04% | 2929.28 | 0
| Tijeras | MW | Don | 2017-10-12 | Herring/Claypool | W (A) | 15032.2959 | 6112.84 | 59.34% | 1587.5386 | 10.56% | 1284.7159 | 0
| Santa Fe | MW | Don | 2017-10-02 | Decker | W | 23819.9654 | 12319.18 | 48.28% | 2198.74 | 9.231% | -247.43 | 0
| ABQ | GL | Chris M | 2017-09-02 | Benedict | B-FR | 14526.5116 | 7382.02 | 49.18% | 1481.68 | 10.2% | 113.31 | 0
| ABQ | JG | Russ T | 2017-10-18 | Beenau | IR | 6334.8837 | 2914.85 | 53.99% | 423.4419 | 6.684% | -420.1163 | 0
| RR | DL | Dennis | 2017-08-16 | Slone | W | 24108.68 | 11927.84 | 50.52% | 3324.92 | 13.79% | 2346.38 | 0
| ABQ | JG | Isaac | 2017-10-09 | Sanchez | B | 6825.1163 | 3899.96 | 42.86% | 653.48 | 9.575% | 619.87 | 0 | Isaac to be charged back an add'l $386.72 + Customer paid for paint: $72.63= $459.35 (Isaac paid 10% of job)
| ABQ | MW | Don | 2017-10-18 | Fernandez | W | 6139.54 | 2976.16 | 51.52% | 718.75 | 11.71% | 323.24 | 0
| ABQ | GL | Chris M | 2017-09-08 | Hagel/Casaus | K | 30251.16 | 18097.98 | 40.17% | 1693.23 | 5.597% | -1845.51 | 0 | Costs were $2972 higher than expected: C-tops 13 sq ft off = $1147. Feb brace not accounted for: $505 cost. THD: $463. CC fees: $490
| Arroya Seco | JG | Chris M | 2017-10-19 | Dalles | B | 11933.4481 | 6257.36 | 47.56% | 907.334 | 7.603% | -584.6519 | 0
| ABQ | GL | Chris M | 2017-09-22 | Walton (GB) | B | 12290.23 | 4607.78 | 62.51% | 1602.26 | 13.04% | 1118.93 | 0 | All 3 contracts are lumped together in LP
| ABQ | GL | Chris M | 2017-09-22 | Walton (MB) | B | 14286.51 | 5477.07 | 61.66% | 1886.63 | 13.21% | 1302.37 | 0 | All 3 contracts are lumped together in LP
| ABQ | LE | Chris M | 2017-09-27 | Eberhardt | B | 11420 | 4697.81 | 58.86% | 1081.31 | 9.469% | -107.97 | 0
| RR | JG | David G | 2017-11-17 | Koeppe | Stucco | 4167.5294 | 2290 | 45.05% | 377.51 | 9.058% | -287.47 | 93.25 | Stucco invoice was verbal ONLY - could not get definitive reason for significant discrepancy
| ABQ | GL | Isaac | 2017-09-13 | Collins | K | 26245.96 | 22311.41 | 14.99% | 1627.2 | 6.2% | -3331.14 | 443.66 | Discounts given: $6250
| ABQ | JG | Isaac | 2017-11-07 | Abeyta | B | 12447.14 | 4789.06 | 61.52% | 1718.685 | 13.81% | 1296.93 | 0
| Alamogordo | JG | Don | 2017-11-02 | Inman | W | 14814.82 | 7383.1 | 50.16% | 1461.89 | 9.868% | 325.52 | 0
| ABQ | LE | Chris M | 2017-08-21 | Myaskorsky | B-FR | 20940.34 | 13916.86 | 33.54% | 987.88 | 4.718% | -2866.46 | 894.41
| Las Vegas | DL | Russ T | 2017-11-28 | Price | Poly | 4899.9961 | 2148 | 56.16% | 626.4981 | 12.79% | 384.9961 | 0
| ABQ | MW | Russ T | 2017-11-30 | Meister | W (A) | 1953.4884 | 784.84 | 59.82% | 204.0842 | 10.45% | 196.4884 | 0
| RR | JG | Marco | 2017-09-13 | Paden | IR | 7548.58 | 3994.66 | 47.08% | 650.29 | 8.615% | 68.58 | 0 | Costs were $220 higher than expected: Flashing needed to be cut back (AC- $130) Plus $121 in CC fees
| ABQ | GL | JJ | 2017-09-22 | Walton | K | 27681.86 | 12836.08 | 53.63% | 2583.73 | 9.334% | 1286.96 | 0 | All 3 contracts are lumped together in LP
| ABQ | MW | Marco | 2017-11-21 | Bartels | IR | 6186.0465 | 3202.14 | 48.24% | 726.3233 | 11.74% | 313.0465 | 0
| Vadito | MW | Don | 2017-10-24 | Leslie | W (A) | 8386.721 | 3593.12 | 57.16% | 1155.4935 | 13.78% | 1451.821 | 0
| ABQ | BS | Don | 2017-10-23 | Garcia / Smart | W (A) | 7395.9567 | 3705.58 | 49.9% | 449.2924 | 6.075% | -119.2433 | 0
| Bosque Farms | JG | Don | 2017-11-21 | Piersol | W | 8201.37 | 4000.55 | 51.22% | 1092.505 | 13.32% | 742.17 | 0
| ABQ | BS | Isaac | 2017-10-31 | Silsbee | B | 13346.9767 | 5486.93 | 58.89% | 1888.5054 | 14.15% | 1513.4767 | 0
| ABQ | DL | Isaac | 2017-10-23 | Busboom | B | 12264.186 | 5568.55 | 54.6% | 1521.809 | 12.41% | 782.226 | 0
| RR | JG | Silvino Campa | 2017-08-02 | Bonura/Sammons | Stucco | 5398.49 | 1700 | 68.51% | 1048.29 | 19.42% | 1314.86 | 0
| ABQ | BS | Rob S | 2017-11-14 | Cory | B | 13287.4419 | 5035.57 | 62.1% | 1779.0621 | 13.39% | 1169.5448 | 0
| ABQ | DL | OTC | 2017-11-15 | Shaver | B | 4062.8272 | 2882.3 | 29.06% | 303.87 | 7.479% | -1111.57 | 667.72 | Costs were $850 higher than expected. (Tile install costs $800 more than priced)
| Santa Fe | TR | Chris M | 2017-11-18 | Casaus | B | 8210.96 | 3634.18 | 55.74% | 1095.4744 | 13.34% | 783.596 | 0
| ABQ | MW | Don | 2018-11-18 | Barela | W (A) | 6637.97 | 2690.39 | 59.47% | 560.2668 | 8.44% | 262.23 | 0
| Tijeras | JG | Don | 2017-08-04 | Costello | W | 42972.64 | 27172.53 | 36.77% | 1204.56 | 2.803% | -7239.1 | 173.44 | Costs were $5686 higher than expected: $2428 spent at THD, not incl door on comm sheet.
| Artesia | BS | Don | 2017-11-22 | Gabaldon | W (A) | 15638.64 | 9163.03 | 41.41% | 823.38 | 5.265% | 1054.14 | 163.04 | Costs were $1343 higher than expected (Hotel 6 nights, not 3, Site check cost: $774.40)
| ABQ | BS | Rob S | 2017-11-24 | Bonano/Jackson | B-FR | 19151.3798 | 7464.24 | 61.03% | 2831.3355 | 14.78% | 2334.2438 | 0
| RR | MW | Russ T | 2017-11-29 | Bulawa | SR-VV | 14706.2245 | 5966.12 | 59.43% | 1874.5623 | 12.75% | 1801.7245 | 0
| ABQ | BS | Isaac | 2017-10-15 | Tolson | B | 10689.3 | 4748.37 | 55.58% | 1318.39 | 12.33% | 667.4 | 0
| ABQ | MW | Marco | 2018-12-16 | Eras | SR-206 | 18600 | 9142.52 | 50.85% | 1906.04 | 10.25% | 1039.1 | 0
| RR | GL | Prime Time | 2017-09-27 | Yonkers | K | 61888.34 | 27320.94 | 55.85% | 8602.09 | 13.9% | 7397.34 | 0
| ABQ | MW | Don | 2018-10-02 | Kraft | D | 11069.77 | 7291.58 | 34.13% | 878.62 | 7.937% | -439.63 | 0 | Stain wasn't to the customer's liking - needed to be restained. (May be an issue w/ Infinity door pricing as well)
| Placitas | JG | Don | 2017-11-13 | Bayse | W | 12230.43 | 6681.92 | 45.37% | 759.92 | 6.213% | -896.57 | 0 | Stucco patch/repair not priced out. ($800 cost)
| ABQ | BS | Isaac | 2017-10-31 | Stock | B-FR | 19984.7811 | 9496.8 | 52.48% | 2444.1506 | 12.23% | 1201.6811 | 0
| Santa Fe | GL | Russ T | 2017-12-08 | Hewitt | B | 9771.7253 | 7836.58 | 19.8% | 850.14 | 8.7% | -122.91 | 117.62 | Job under sold. Too few trip charges, flooring miscalculation, C-top miscalculation, didn't consider tape/texture in pricing.,
| ABQ | ME | Chris M | 2018-09-16 | Jiron | B-FR | 16081.43 | 5990.92 | 62.75% | 1602.07 | 9.962% | 4033.73 | 0 | 2nd half not paid out.
| Tijeras | ME | Rob S | 2017-10-17 | Drown | B | 5920.4638 | 2585.34 | 56.33% | 448.39 | 7.574% | 805.5638 | 0 | 2rd half not paid out.
| Artesia | JG | Don | 2017-11-09 | Delgado | W (A) | 8584.35 | 4423.86 | 48.47% | 886.15 | 10.32% | 1247.48 | 0
| Roswell | BS | Chris M | 2017-11-05 | Gordo | B-FR | 21086.71 | 11691.38 | 44.56% | 1773.77 | 8.412% | 247.25 | 0 | Costs were $1114 higher than expected: Add'l hotel and travel charges
| ABQ | JG | Marco | 2017-12-30 | Schriner | IR | 9353.0794 | 5217.33 | 44.22% | 681.2197 | 7.283% | -337.7206 | 0 | CJT elec did extra work, invoiced us, Plus raised prices that we have not accounted for.
| ABQ | MW | Marco | 2017-07-11 | Limon | SR-VV | 30697.67 | 13895.03 | 54.74% | 2865.74 | 9.335% | 1083.47 | 0
| ABQ | GL | Isaac | 2017-12-14 | Gagon/Olson | B | 11710.6977 | 6309.24 | 46.12% | 1729.9688 | 14.77% | 1440.9977 | 0 | Add'l invoices after costing
| ABQ | GL | Rob S | 2017-12-29 | Tollestrup (MB) | B-FR | 25387.907 | 8857.25 | 65.11% | 3077.2163 | 12.12% | 1546.0015 | 0
| ABQ | BS | Chris M | 2017-12-13 | Garcia | B | 10335.814 | 4700.15 | 54.53% | 1110.71 | 10.75% | -263.418 | 200 | Margin did much better than front half suggested (Old ONYX pricing)
| ABQ | TR | Chris M | 2017-10-17 | Aragon | B-FR | 19560 | 10043.72 | 48.65% | 2002.02 | 10.24% | 158.8 | 0 | Had a few "issues" w/ sollid cabs - Extra costs associated.
| ABQ | GL | Prime Time | 2017-12-26 | Skidmore | K | 28394.4186 | 19940.52 | 29.77% | 1599.4 | 5.633% | -830.27 | 0 | Costs were $5743.31 higher than expected: C-top not priced correctly, Gas line, CC fees, Installer damaged OC
| ABQ | GL | Rob S | 2017-12-29 | Tollestrup (GB) | B | 14515.3488 | 5821.11 | 59.9% | 2158.23 | 14.87% | 724.1518 | 500
| Alamogordo | JG | Isaac | 2017-10-31 | Acevedo | B-FR | 17075 | 10611.72 | 37.85% | 1732.59 | 10.15% | 637.6 | 0 | Wall panels ordered short for 2nd bath - add'l cost TTL: 1321.80 (labor) + 825.78 (Materials) = 2147.58
| Los Alamos | MW | Don | 2017-09-09 | Iverson | W | 41467.68 | 23952.45 | 42.24% | 4735.76 | 11.42% | 2052.78 | 0 | Western wall did stucco, customer not happy had to be re-done TTL stucco cost: $5,283.81
#REF!

## Product Margin Analysis
Category | Product | Average margin by product
Kitchen & Bath | B | 53.16% | 53.16%
| K | 40.71%
Patio Covers | FP | 49.96%
| IR | 48.02%
| LC | 49.82%
| OP | 38.45%
| VP | 55.22%
Sunroom | SR-206 | 62.34%
| SR-306 | 51.58%
| SR-406 | #DIV/0!
| SR-VV | 58.91%
| SCR-WO | #DIV/0!
Windows | D | 47.64%
| W (A) | 51.77%
| W | 48.69%
Overall average |  | 66.47%
Category |  | Average margin
Kitchen & Bath |  | 46.94%
Patio Covers |  | 48.3%
Sunroom |  | #DIV/0!
Windows |  | 49.37%
Overall average |  | 66.47%

## Product Revenue Analysis
Category | Product | Net Sale | Average Sale
Kitchen & Bath | B | 667787.8258 | 9539.8261 | 66778783%
| K | 376306.7486 | 26879.0535
Patio Covers | FP | 79420.33 | 6618.3608
| IR | 340490.0596 | 9728.2874
| LC | 140698.0362 | 6395.3653
| OP | 63440.79 | 15860.1975
| VP | 68401.83 | 7600.2033
Sunroom | SR-206 | 80461.08 | 16092.216
| SR-306 | 246767.3 | 30845.9125
| SR-406 | 0 | #DIV/0!
| SR-VV | 113884.8045 | 14235.6006
| SCR-WO | 0 | #DIV/0!
Windows | D | 76687.88 | 5477.7057
| W (A) | 148952.6921 | 7447.6346
| W | 399318.2154 | 14789.5635
Overall average |  | 2802617.5922 | #DIV/0!
Product by classification |  | Net Sale | Average Sale
Kitchen & Bath |  | 1044094.5744 | 18209.4398
Patio Covers |  | 692451.0458 | 9240.4829
Sunroom |  | 441113.1845 | #DIV/0!
Windows |  | 624958.7875 | 9238.3013

## Installer Analysis
Category | Installer | Average Margin
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
|  | #DIV/0! | #DIV/0!
#DIV/0!
#DIV/0!
Total Margin |  | 66.47%
Kitchen & Bath
PC & SR
Uncategorized
Windows

## Designer Analysis
Designer | Total sales | Total # of sales | x̅ Sale | x̅ Margin | x̅ Comm % | x̅ Over/Under | Total additional incentive | x̅ Additional incentive
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0!

## Sales Location Analysis
Location | Total sales | Total # of sales | x̅ Sale | x̅ Margin | x̅ Over/Under
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!

## Sales by month
Designer | Total sales | Total # of sales closed | Average Sale | Average Margin
2017-01-01 | 124302.94 | 16 | 7768.9337 | 48.87%
2017-02-01 | 298163.24 | 23 | 12963.6191 | 51.32%
2017-03-01 | 387644.87 | 37 | 10476.8884 | 52.1%
2017-04-01 | 586706.1 | 37 | 15856.9216 | 48.04%
2017-05-01 | 284416.5514 | 28 | 10157.734 | 48.82%
2017-06-01 | 312020.5068 | 30 | 10400.6836 | 52.73%
2017-07-01 | 203636.55 | 20 | 10181.8275 | 53.83%
2017-08-01 | 285887.5647 | 23 | 12429.8941 | 48.06%
2017-09-01 | 479018.6116 | 25 | 19160.7445 | 51.51%
2017-10-01 | 214317.6821 | 20 | 10715.8841 | 51.54%
2017-11-01 | 173746.3553 | 17 | 10220.3738 | 51.26%
2017-12-01 | 109468.9907 | 7 | 15638.4272 | 45.64%
| 3459329.9627 | 283 | 12223.7808 | 66.47%
Formulas:
Total sales = SUMIFS('Raw Data'!$I5:I500,'Raw Data'!$F5:F500,">="&[Designer],'Raw Data'!$F5:F500,"<="&EOMONTH([Designer],0))
Total # of sales closed = COUNTIFS('Raw Data'!$F5:F500,">="&[Designer],'Raw Data'!$F5:F500,"<="&EOMONTH([Designer],0))
Average Sale = SUMIFS('Raw Data'!$I5:I500,'Raw Data'!$F5:F500,">="&[Designer],'Raw Data'!$F5:F500,"<="&EOMONTH([Designer],0))/COUNTIFS('Raw Data'!$F5:F500,">="&[Designer],'Raw Data'!$F5:F500,"<="&EOMONTH([Designer],0))
Average Margin = SUMIFS('Raw Data'!$K5:K500,'Raw Data'!$F5:F500,">="&[Designer],'Raw Data'!$F5:F500,"<="&EOMONTH([Designer],0))/COUNTIFS('Raw Data'!$F5:F500,">="&[Designer],'Raw Data'!$F5:F500,"<="&EOMONTH([Designer],0))